## Slide 1: Design for Verification Project Update
2021-06-30
Eldrick Millares, Jack Humphries (eldrick, jhumphri@stanford.edu)

## Slide 2: Recap:
Deploying “External QED” to Steelcore
Running initial tests with control flow
Started deploying on CVA6 (Ariane)
Found the extremal bug generator script

## Slide 3: External QED - Progress
Implemented “memory shim” and integrated into design
No control flow - only arithmetic, memory load/store
Changes from original QED so far:
  Instantiated separate instruction memory
  Added in initial “boot address” constraint for PC
  Extended Tc later to account for initial fetch cycles, longer pipeline

## Slide 4: External QED - Issues
Implementation still ongoing
Current Issues:
  Duplicate instructions not being issued
  Much longer proof bounds
    Previous: Hours for 3-6 instructions
    External QED: Jumps from 4 to 16 to 18 within minutes

## Slide 5: External QED - Proof Radius Issue

## Slide 6: Control Flow
Jack pushed his modifications to sqed-generator that includes jump instructions
Need to clean up some small syntax errors from generator

## Slide 7: CVA6
Started deploying to CVA6
6 Stage pipeline, System Verilog, capable of booting Linux
More complex ISA (RV64IMAC), more complex uarch
3rd most popular RISC-V core by # of Github Stars

## Slide 8: CVA6
Currently trying to figure out how to structure top level
All memory, peripherals connected via AXI interface

## Slide 9: Extremal Bug Script
Located in /scratch0/nuthakki/ridecore-master/ridecore-master/src/ride-with-2QED-sss/logic-results-ride-with-2QED-sss-withlw-srcforw/sim_logic_bugs/results-100-rand-indsim-sim-priority/sim_projects-144481-1
Found scripts related to launching simulation, saving state at some point in time, etc
Thank you to Florian for following up with Eshan

## Slide 10: Per Week Summer Schedule
Jun 28 Add Control Flow Instrs. to Steel
Jul 05 Basic External QED on Steel
Jul 12 ...
Jul 19 Finish Deploying on CVA6

## Slide 11: Summer Workload
May need to step back summer commitment
Excited about project, plan on developing in free time
Am planning on taking only research units in Fall